## 2024
Remediation Action | Responsible Party | Initial Date | Target Date | Completion Date | Status
Replace dumpster pad between Reagan and Flowers | Victor | 2022-06-23 | 2025-06-30 | N/A | Needs to be re-quoted - Victor to reach out
Security measures for ILP, SJAB, Cobb, & Cottages - Cameras | Victor, David, LuAnne, Tabatha | 2022-06-23 | 2025-06-30 | N/A | Deposit placed on new camera system. Installation complete March 2025 Training on new system and system launch scheduled end of March 2025
Upgrade lighting behind Cobb Center | Victor | 2022-09-14 | 2025-07-30 | N/A | Victor will look into possible lighting upgrades . Has received quotes, Waiting to see if the cameras provide any additional lighting once installed
Chapel Lighting/Exit Signs Inspection | Victor | 2024-06-12 | 2025-03-31 | NA | Victor to inspect and address issue by end of the year
SJAB Dock Light Sensor Installation | Victor | 2024-06-12 | 2025-03-31 | NA | Victor to investigate and install SJAB dock light sensor
Cobb Floor Repair | Victor | 2024-12-11 | 2025-06-01 | N/A | Victor to have floor repaired
Medication Room Lock | Victor | 2024-12-11 | 2025-03-31 | N/A | Victor to put new door knob and lock on medication room door
Security measures for ILP, SJAB, Cobb, & Cottages - Key Cards for ILP | Victor, David, LuAnne, Tabatha | 2025-03-12 | 2026-06-30 | N/A | To possibly be implemented in next years (2026) budget. Will most likely begin trial with ILP Cottages
SJAB Ramp | Victor | 2025-03-12 | 2025-05-31 | N/A | Victor to have ramp installed at the front entrance of SJAB building
1 Year MHCO Food Supply Storage | Darauna | 2025-03-12 | 2025-06-30 | N/A | Darauna to order non perishables for storage

## Completed Risk Management List
Remediation Action | Responsible Party | Initial Date | Target Date | Completion Date | Status
Fence repair on Forest Avenue | Victor | 2016-07-01 | N/A | 2018-07-05 | Completed
Electrical covers for light poles replacement | Victor | 2020-09-25 | N/A | 2020-10-15 | Completed
Tree pruning and removal plan | Victor | 2017-07-01 | 2019-06-30 | 2020-12-30 | Completed per 3-year plan
Security Officer | Kevin | 2020-09-25 | N/A | 2021-04-12 | Completed
Replace doors at SGA, GYM, and food room elevator, compressor room at dock | Victor | 2017-07-01 | 2019-06-30 | 2021-12-30 | Completed
Pool bathroom floors | Wendi/Amy | 2019-07-01 | 2020-06-30 | 2022-05-15 | Completed
Cottage cell phones/tablet | Tabatha/LuAnne | 2020-09-25 | 2022-07-31 | 2022-08-24 | Completed
Camera Notice and No Trespassing Signage | Kevin/Gene/David | 2022-07-27 | 2022-09-30 | 2022-09-19 | Completed
Restroom Door Locks Needed in Gym | Victor | 2022-09-14 | 2022-10-05 | 2022-10-03 | Completed
File Cabinet Labels | Kat | 2022-09-14 | 2022-12-31 | 2022-09-21 | Completed
Camera Battery Backups Installed | Tabatha | 2022-12-14 | 2022-12-31 | 2022-12-29 | Completed
Lockdown Procedures & Active Shooter Training | Linda M./David | 2022-07-27 | N/A | 2022-12-13 | Completed
SJAB front step - ramp or caution strip | Victor/LuAnne | 2022-06-23 | N/A | 2023-03-22 | Completed
Repair loose Rails going into Brown Steps | Victor | 2022-09-14 | 2022-12-31 | 2022-10-03 | Completed
Purple "No Hunting" Paint Behind Farm | Victor | 2022-09-14 | 2022-12-31 | 2023-01-30 | Completed
Damaged Sprinkler Repair | Victor | 2022-12-01 | 2023-01-30 | N/A | Completed
Surge Protector Safety Reminders to Cottages | Victor/Tabatha | 2022-12-13 | 2023-01-30 | 2023-03-22 | Completed
Signage to prevent public from walking on lower campus and farm | Gene/Victor | 2022-12-13 | 2023-04-30 | 2023-02-01 | Completed
Repair loose wheelchair ramp rails in Brown | Victor | 2022-09-14 | 2023-06-23 | 2023-04-30 | Completed
Road repair on farm | Victor | 2022-07-27 | 2023-04-15 | 2023-05-23 | Completed
Road repairs on campus | Victor | 2022-07-27 | 2023-10-01 | 2023-06-09 | Completed
Document scanning of old/outdated medical and program files | Amy Still | 2022-06-23 | 2023-09-30 | 2023-08-31 | Completed
Replace damaged ceiling tiles in Food Room due to mildew | Victor | 2023-03-22 | 2023-07-30 | 2023-06-15 | Completed
Lighting needed between gym & SGA (stairs) | Victor | 2023-03-22 | 2024-09-30 | 2024-08-30 | Completed
Lighting needed by ceramics room | Victor | 2023-03-22 | 2024-09-30 | 2024-08-30 | Victor will look into possible lighting upgrades, waiting on electrician survey
Lighting needed by ceramics room | Victor | 2023-03-22 | 2024-09-30 | 2024-08-30 | Completed
Determine additional installation of cameras (campus, vans, and cottages) | Victor/David/LuAnne/Tabatha | 2021-03-01 | 2024-12-31 | 2024-11-15 | Completed
Extend Forest Avenue Fence | Victor/LuAnne | 2024-12-31 | 2024-12-31 | 2024-11-30 | Completed
Walk in cooler Issues | Victor/LuAnne | 2024-06-12 | 2024-12-31 | 2024-11-27 | Completed